# Proofit — Progress Log, Phases 0–2

Owner: Person B   ·   Compiled: 15 Sep 2026   ·   Semester week: 2 of 15

This log records what has actually shipped against PERSON_B_PLAN_v2.md, phase by phase, including what was skipped or deferred. It is written to be checkable: every “done” claim below corresponds to a file in the repo, a commit, or a command that can be re-run.

Where a planned deliverable is not done, it says so plainly rather than omitting it.

# 1. Schedule position

|  | Planned | Actual |
| --- | --- | --- |
| Phase 0 — Foundation | Weeks 1–2 (7–20 Sep) | Substantially complete |
| Phase 1 — Fixtures, types, shell screens | Weeks 3–4 (21 Sep–4 Oct) | Substantially complete |
| Phase 2 — Results experience | Weeks 5–7 (5–25 Oct) | Complete, except the two CP2-blocked tasks |

The build is running roughly seven weeks ahead of the plan’s calendar. Today is Week 2, which the plan schedules as mid-Phase-0; Phase 2’s own deadline is 25 Oct.

That headroom is real, but it is not uniformly distributed. The work that ran ahead is the code; the work that lagged is the human-dependent, calendar-bound work — collecting consented resumes, drawing wireframes, showing them to classmates, standing up live hosting. Those cannot be compressed the way code can, and several of them gate later phases (§5). The honest summary is: implementation is far ahead, field and logistics work is behind.

A second caveat: git history does not corroborate the Phase 0/1 timeline. All Phase 0 and Phase 1 work was committed in two commits on 14 Sep (d42067a, 63614ce), so the repo cannot evidence when it was built. Phase 2 (26 commits, 14–15 Sep) is fully traceable.

# 2. Phase 0 — Foundation

Goal: every decision written down, both machines run the stack locally, hosting exists, data collected. No product code.

| # | Deliverable | Status | Evidence / gap |
| --- | --- | --- | --- |
| 1 | Brand, BRAND.md | Done | BRAND.md — positioning, voice rules (§6), colour tokens. Design system later pivoted from indigo to the paper/ink/lac palette now in use. |
| 2 | Monorepo scaffold | Done | web/ (Next.js 15, App Router, TS strict, Tailwind), api/ (FastAPI + pydantic-settings), engine/ (installable package, pyproject.toml) |
| 3 | Local dev via Docker Compose | Done | deploy/docker-compose.yml, api/Dockerfile, deploy/runbook.md. Note: Colima must be started manually on the dev machine. |
| 4 | i18n skeleton | Done | next-intl, app/[locale]/ routing, messages/en.json + km.json, locale switcher in header |
| 5 | Design system + primitives | Done | Button, Card, Badge, Stamp, VerdictIcon, CoverageStat. Verdict colours always paired with an icon, never colour alone. |
| 6 | Wireframes + classmate feedback | Not done | docs/wireframes/ contains only a README, which states this plainly. No images, no feedback round. |
| 7 | Hosting accounts + first deploy | Not done | deploy/render.yaml and the runbook exist; no live URL is recorded anywhere in the repo. |
| 8 | Data collection (15 JDs, 5 resumes) | Partial | See below — JDs exceeded in volume but skewed; resumes well short. |
| 9 | .env.example, secrets discipline | Done | .env.example present, .env git-ignored, no keys committed |

## Data collection, in detail

Job descriptions — 25 unique real listings collected (44 CSV records across four files, with overlap between them), past the 15 the plan asked for in raw volume:

| Source | Records | Country | Records |
| --- | --- | --- | --- |
| CamHR | 24 | KH | 38 |
| BongThom | 14 | REMOTE | 3 |
| RemoteOK | 3 | unlabelled | 3 |
| Arbeitnow | 3 |  |  |

Two qualifications matter more than the headline count:

- The geographic mix does not match the demo story. The plan asked for 5 local, 5 Singapore/Japan/Australia, 5 remote-US. Actual: 38 Cambodian, 3 remote, and zero Singapore, Japan, or Australia listings. F6 (country rules) and the cross-border differentiator both depend on JDs that have not been collected.

- The three individual JD files are synthetic. data/jds/*.txt are hand-written stand-ins — source.json flags each with “synthetic”: true and the note “Hand-written stand-in until real JDs are collected”. The golden fixtures, and therefore every demo and screenshot to date, are built on these rather than on the 25 real listings sitting in the CSVs.

Resumes — 1 of 5. data/resumes/anonymized/candidate_a.txt only; raw/ is empty. eval/consent_form.md exists as a bilingual template but is unsigned and unfilled. The plan explicitly notes these consents are reused for the Phase 6 evaluation study.

# 3. Phase 1 — Fixtures, Types, Shell Screens

Goal: build every screen without Person A’s engine existing, so the engine slots in with zero UI changes when it lands.

| # | Deliverable | Status | Evidence / gap |
| --- | --- | --- | --- |
| 1 | CP1 — schema locked with Person A | Provisional | engine/normalize/schema.py exists and is the working contract, marked 0.1.0-provisional. Not yet jointly locked in a CP1 session. |
| 2 | Generated TypeScript types | Done | scripts/gen-types.sh → web/lib/schema.json → web/lib/types.ts (generated, never hand-edited). CI workflow present (.github/workflows/ci.yml). |
| 3 | Three golden fixtures + validation test | Done | data/fixtures/{fresh_grad_strong_fit,fresh_grad_stretch,unrealistic}.json, validated by tests/test_fixtures.py (schema conformance, verdict-per-requirement, distinct realism verdicts) |
| 4 | FastAPI mock mode | Done | ENGINE_MODE=mock¦live; POST /api/resumes, POST /api/jobs, POST /api/analyses, GET /api/analyses/{id}; in-memory store, BackgroundTasks, artificial delay so loading states are honest |
| 5 | Screens v0 (Landing, Analyze, Results) | Done | Five screens built: Landing, Analyze, Progress, Results, About |
| 6 | i18n discipline | Partial | scripts/i18n-check.mjs enforces key parity and reports 0 errors. The planned ESLint rule failing CI on raw JSX string literals was not added. |
| 7 | First real deploy + keep-alive | Partial | .github/workflows/keepalive.yml exists; no live deployment. |

Carried into Phase 2: the mock store is explicitly non-durable (in-memory, resets on process restart) and is scheduled for replacement by Supabase at CP2.

# 4. Phase 2 — The Results Experience

Goal: finish the screen the examiner will stare at, before the engine behind it exists.

Executed as a written 13-task plan (docs/superpowers/plans/2026-09-14-phase-2-results-experience.md), one task at a time, each with an independent review before the next began, plus a final whole-branch review. 26 commits, merged to main at efe489a.

## What shipped

Error handling — a real contract, not ad-hoc messages. docs/errors.md had specified a ten-code error contract before any of it was built; Phase 2 implemented it. A typed ApiError (api/errors.py) now produces one envelope everywhere — {"error": {"code", "message", "error_id"}} — and every route raises it (no bare HTTPException remains anywhere in api/routes/). The frontend switches on code, never on message text, and renders localized copy from a new ten-key errors.* catalogue. Each code routes to the right place in the UI: file-type and size rejections appear inline under the resume dropzone, empty-job-post errors under the JD tabs (with focus moved to the field), a missing analysis gets a full-page state with a way back, and an engine failure gets an error card carrying Retry and a copyable error id.

Keyword-baseline comparison — the evaluation chapter’s argument, made visible. Hand-authored TF-IDF baseline fixtures now pair with each golden fixture (separate sibling files; the schema forbids extra keys, so they could not be merged in). A results-screen toggle shows the naive matcher’s verdict beside the real engine’s for every requirement, plus both aggregate scores side by side.

Evidence-type storytelling — the product’s core differentiator, stated on screen. When a requirement is only partly proven by a class project, coursework, or part-time work, the UI now explains why it counts partially and not fully — in the register BRAND.md §6 prescribes: name the claim and its limit in the same breath.

Progress stepper — three honest states instead of one dead end. A real 120-second client-side ceiling, distinct from a server-reported failure. Hitting the ceiling offers “keep waiting” (the analysis may still finish) rather than discarding work; a genuine failure offers Retry against a new POST /api/analyses/{id}/retry endpoint that reuses the original resume, job, and country, so nothing is re-uploaded.

Recovered work. A “remember the last uploaded resume” feature had been built earlier but never committed, and was stranded outside the working branch. It was recovered and re-merged.

## A finding worth carrying into the report

The baseline comparison was expected to show the engine beating naive keyword matching everywhere. Derived honestly and consistently, it does not: on fresh_grad_strong_fit the engine leads by 19.2 points, but on fresh_grad_stretch the gap narrows to 2.5, and on unrealistic the naive matcher actually outscores the engine by 4.2.

This is not a defect. Those two postings demand depth — years of professional production experience, CI/CD pipelines — while the candidate’s resume happens to contain the words “React”, “API”, and “pipeline” from unrelated class projects. A keyword matcher cannot tell a class project from two years of paid work; the engine’s F4 rules correctly refuse the credit. The naive matcher does not merely lose — on demanding postings it misleads the candidate into believing they are a better fit than they are — which is a stronger argument for requirement-level matching than a uniform win would have been.

The test suite now asserts this pattern directly rather than a “baseline always loses” invariant, and web/lib/fixtures/sample-baseline.ts documents the derivation rule so the numbers can be defended under questioning.

## Deliberately out of scope

Two of the plan’s seven Phase 2 tasks were not attempted:

- Wire the live engine (CP2). engine/match/run_match and run_baseline both still raise NotImplementedError — they are Person A’s, and unfinished. There is nothing to wire. engine/ was left completely untouched by this phase.

- Deploy live mode. Follows the above.

Both are picked up at CP2. Everything else in Phase 2 was built against mock mode, which is exactly what the phase was designed to allow.

## Quality state at merge

| Check | Result |
| --- | --- |
| Backend tests | 27 passed, 0 failed |
| Frontend typecheck (tsc --noEmit) | Clean |
| Lint (eslint .) | 0 errors (1 pre-existing warning in generated types.ts) |
| i18n key parity | 128 keys, 0 errors |

Four genuine bugs were caught and fixed during review that automated checks would not have found — two of them defects in the plan’s own prescribed code: a fixture-pairing bug that would have compared a resume against one job’s baseline and another job’s match, and a “keep waiting” button that would have silently done nothing. The other two: a test that passed without exercising the code it claimed to test, and developer-facing error strings reaching users.

# 5. Outstanding items, in priority order

Ordered by how much they gate later work, not by effort.

- Collect consented resumes (4 more). Phase 6’s evaluation study depends on these, and the plan says to book raters in Week 11 — but the resumes must exist first. The consent template is ready; this is purely a matter of asking classmates. Longest lead time of anything on this list.

- Collect Singapore / Japan / Australia JDs. Currently zero. F6 country rules and the cross-border differentiator — a headline claim on the landing page — have no data behind them.

- CP1 — lock the schema with Person A. Currently provisional. Everything downstream depends on it, and the longer it stays unlocked the more expensive a change becomes.

- Stand up the live deployment. Vercel + Render, per deploy/runbook.md. The plan wanted a live URL in the proposal document; the keep-alive workflow is already written and waiting for something to keep alive.

- Rebuild the fixtures on real JDs. The demo currently runs on synthetic stand-ins. Twenty-five real listings are already collected and unused.

- Draw the wireframes and run the classmate feedback round. Five screens are already built, so this is now partly retrospective — but the feedback round still has value, and the plan counts it as a deliverable.

- Add the raw-JSX-string ESLint rule so i18n discipline is enforced by CI rather than by habit.

## Known minor items, deliberately deferred

Roughly two dozen minor findings were raised during Phase 2 reviews and consciously parked as non-blocking — a duplicated coverage label, a doc clause broader than the behaviour it describes, a missing regression test for one recently fixed edge case. They are recorded in the commit history and the plan document. None affect correctness.

One larger deferred item worth naming: web/messages/km.json contains no actual Khmer. All 128 keys are byte-identical to the English. This is intentional and tracked — docs/errors.md §4 and the plan both schedule a Khmer QA session with Khmer-first speakers for Phase 5 — but it does mean the bilingual claim is currently structural, not substantive.

# 6. Next checkpoint

CP2 — wire the live engine. Blocked on Person A delivering run_match / run_baseline. When it lands, the work is: flip ENGINE_MODE=live, call the contract functions from the background task, replace the in-memory store with Supabase, and reconcile any place the live output differs from the fixtures — fixing the fixture, never the UI.

The whole point of Phase 2’s mock-mode design is that this is a single integration step rather than a rebuild. Until then, Phase 3 work (URL ingestion, analysis history, and the F5 rewrite engine — which is Person B’s to build, not Person A’s) can proceed independently.